{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"read":"whole","date_system":"1904","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":24,"n_cols":6,"rows_kept":24,"merged":[[0,3,0,5],[1,0,1,2]],"flags":["formulas_cached_only"]}
[{"$nulls":3},"timm says"]
["Jairus says",null,null,"strategic guidance (requires long term planning)","tactical guidance (can change in a project)","wild (I.e. not controllable)"]
["COCOMO II Scale Factors","prec","pick partners and new projects based on doing what you alrady know how to do. For exampel JPL is the tops at EDL. ","y"]
[null,"flex","negotiate for flexible requirements",null,"y"]
[null,"resl","manage your risks wel. I would argue this is process related but you could chosse to do a better job. ",null,"y"]
[null,"team","how well functiona s a team.  Shows value fo high quality open communication.  Cannot control this always but can seek ita nd foster it.",null,null,"y"]
[null,"pmat","This is only changed over the longer run.  An individual project cannot really manipulate this as a variable.  It could show payoff of investment in process improvement. Or could use it to argue never higher a contractor that is not at least Level 3.","y"]
["COCOMO II Drivers Can either give the COCOMO II rating (e.g. low, nom, high+25, verylow+50), or give us the value (such as .80, 1.00, 1.12, .75). Just be consistent.","rely","usually not variable.  Determined by application for example Human is VH, Flight is High, Ground is Nom mostly but can be H.",null,null,"y"]
[null,"cplx","This largely determined by application but many people here argue that a good system architecture can greatly reduce the complexity so could be used measure payoff of spedning a bit more upfront for a better design.",null,"y"]
[null,"data","amount of test data.  I think this is application and customer dependent. ",null,"y"]
[null,"docu","This can be negotiated",null,"y"]
[null,"ruse","desing for future reuse.  This ioncreases cost.  But is suppose to save money for future developemnt projects.  Is alsoa  key variable in looking at product lines.",null,"y"]
[null,"time","these 2 depend on wether there is aconstarin on your HW which can happen on spacecraft",null,null,"y"]
[null,"stor",null,null,"y"," "]
[null,"pvol","Mostly becomes bad due to new major products or releases. For rexample no one wants to buy VISTA right now.",null,null,"y"]
[null,"acap","All the people ones can be manipualted to large extent.  However, in a ","y"]
[null,"pcap","large company often have to picj from an existing pool and problem at ","y"]
[null,"pcon","JPL is that mutliple projects all fight over the top people.","y"]
[null,"apex",null,"y"]
[null,"plex",null,"y"]
[null,"ltex",null,"y"]
[null,"tool","project often choose tools but if it is the very first time the model somewhat lies as they often increase cost until get through the learning curve and then save money in the long run. ",null,"y"]
[null,"site","colocation unless your partner is forced on you as ESA this can be controlled by project.","y"]
[null,"sced","can be nogotiated",null,"y"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}